## Iteration 1 Plan
Iteration Plan 1
Project | Indie Fusion
Team Names: | Sruthi Kamisetti, Twinkle Mishra, Naina Jagiasi
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | The initial UI for Register,Login,Forgot Password and Reset Password has been completed, outlining all essential tasks and priorities. However, further refinement and polishing of the wireframe are needed to enhance its clarity and user experience before moving forward. | SK/NJ | Yes
2 | Integrate external libraries for React Router for routing, React Bootstrap for styling components, ensuring responsive design | SK | Yes
3 | Create Registration Feature for new users (artists/clients). Collect required data and handle form validation. | SK/TM | Yes
4 | Create Login functionallity allowing users(Artist/Clients) to sign into their accounts and implement form validation and error handling for login credentials | NJ/TM | Yes
5 | Implement the fogot password feature, where the user can request a password OTP to the email. Validate user OTP and update password | SK/TM | Yes
6 | Develop the rest password feature,allowing user to set the new password with validation. | NJ/TM | Yes
7 | Setup the backend environment using Nodejs or Java and configure the server, middelware and establish the database connection using MongoDB. | TM | Yes
8 | Develop API endpoints for handling user data such as register,login and password management. | TM | Yes
9 | Perform manual testing on all frontend features(Register,Login,password reset and Forgot Password) to ensure proper functionality and user experience. | SK/TM/NJ | Yes
10 | Test frontend and backend integration to validate successful communication. | SK/TM/NJ | Yes
11 | Document any bugs or issues found during testing and prepare them for next iteration or fix them before iteration. | SK/TM/NJ | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
React.js for Frontend | Current Concern:Performance issues may raise with complex component states and re-renders. Potential Concern: Difficulty in maintaining across multiple components as the application grows. | SK/NJ
MongoDB for database | Current Concern: Schema design can lead to data inconsistency if not carefully planned. Potential Concern: Might be challenging for data retrieval performance for large datasets when application grows. | TM/SK
Node.js/Java for Backend | Still under discussion. | TM
Solution Design | Ensuring seamless communication between frontend,backend and database could be challenging. | TM/SK/NJ
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Microsoft Project Planner | Useful for project scheduling and Gantt charts.
Jira | Jira is helpful for tracking issues, managing agile projects, and promoting teamwork with its customizable workflows and reporting features.

## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | Refining and polishing of wireframe. | 0.75 | SK/NJ
102 | Integrate external libraries for React Router for routing, React Bootstrap for styling components, ensuring responsive design | 0.25 | SK
103 | Registration Module (UI design, API development, API + UI Integration) | 5 | SK/TM
104 | Login Module (UI design, API development, UI + API Integration) | 4 | NJ/TM
Medium Priority (light blue)
105 | Forgot Password Module (UI design, API development, UI + API Integration) | 4 | SK/TM
Low Priority (pink)
106 | Reset Password Module (UI design, API development, UI + API Integration) | 4 | NJ/TM

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Refining and polishing of wireframe. | 0 | 0.75 | 0 | 0 | 0
102 | Integrate external libraries for React Router for routing, | 0 | 0.15 | 0 | 0 | 0
103 | React Bootstrap for styling components, ensuring responsive design | 0 | 0.1 | 0 | 0 | 0
104 | Registration Module Frontend UI design | 0 | 2 | 0 | 0 | 0
105 | Registration Module API development | 0 | 1.5 | 0 | 0 | 0
106 | Registration Module Frontend-Backend Integration | 0 | 1.5 | 0 | 0 | 0
107 | Login Module Frontend UI design | 0 | 1 | 0 | 0 | 0
108 | Login Module API development | 0 | 1.5 | 0 | 0 | 0
109 | Login Module Frontend-Backend Integration | 0 | 1.5 | 0 | 0 | 0
110 | Forgot Password Module Frontend UI design | 0 | 1.5 | 0 | 0 | 0
111 | Forgot Password Module API development | 0 | 1 | 0 | 0 | 0
112 | Forgot Password Module Frontend-Backend Integration | 0 | 1.5 | 0 | 0 | 0
113 | Reset Password Module Frontend UI design | 0 | 1.5 | 0 | 0 | 0
114 | Reset Password Module API development | 0 | 1 | 0 | 0 | 0
115 | Reset Password Module Frontend-Backend Integration | 0 | 1.5 | 0 | 0 | 0
116 | Implemented server-side logic to handle logout, including session or token validation and clearing session data on the client-side. | 0 | 0.25 | 0 | 0 | 0
117 | Verify that the logout button functions correctly, ensuring the user is logged out, redirected to the login page, and session data is cleared. | 0 | 0.25 | 0 | 0 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 74 | 0 | 0 | 0
Total Project Hours |  | 74

## Iteration 2 Plan
Iteration Plan 2
Project | Indie Fusion
Team Names: | Sruthi Kamisetti, Twinkle Mishra, Naina Jagiasi
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | Design and create wireframes for Artist Profile Page to establish a visual guide for development. | TM,NJ | Yes
| Design and create wireframes for Landing/Home Page to establish a visual guide for development. | TM,NJ | Yes
2 | Implement the core functionality for the Artist Profile Page using React, ensuring users can easily interact with their profiles. | TM, NJ | Yes
3 | Develop and deploy backend APIs utilizing Node.js to facilitate user profile creation and data management. | SK | Yes
4 | Establish MongoDB tables specifically designed for the efficient storage of artist profile data. | SK | Yes
5 | Perform manual testing on the profile creation functionality to verify that all features are working. | All | Yes
6 | Build and implement functionality for users to edit their profiles using React, allowing for a seamless user experience. | TM | Yes
7 | Create a user-friendly interface for the Edit Profile feature using React, ensuring intuitive navigation and accessibility. | TM, NJ | Yes
8 | Develop backend APIs to support the editing of user profiles, allowing for smooth data updates in the database. | SK | Yes
9 | Set up MongoDB tables that accommodate the necessary updates for artist profiles, maintaining consistency with previous data. | SK | Yes
10 | Conduct manual testing to confirm that the editing functionality works correctly, ensuring users can modify their profiles without issues. | All | Yes
11 | Build functionality for post creation using React, enabling users to share content on the platform. | TM, NJ | Yes
12 | Create backend APIs using Node.js to manage the creation of posts, ensuring that data is processed and stored securely. | SK | Yes
13 | Set up MongoDB collections specifically for storing posts details. | SK | Yes
14 | Perform manual testing of the post creation feature to ensure that users can successfully create posts without errors. | All | Yes
15 | Design a wireframe for the Landing/Home Page, creating a blueprint for the layout and essential features. | NJ | Yes
16 | Develop the user interface for the Landing/Home Page using React, incorporating design elements that enhance user engagement. | NJ, TM | Yes
17 | Create backend APIs to support the functionality of the Landing/Home Page, ensuring dynamic content delivery and user interactions. | SK | Yes
18 | Execute manual tests to validate the functionality of the Landing/Home Page, ensuring all elements work seamlessly together. | All | Yes
19 | Integrate the frontend and backend systems for the Profile Creation feature, guaranteeing smooth user experience and data flow. | SK | Yes
20 | Integrate frontend and backend systems for the Post Creation feature to ensure a cohesive experience for users when sharing content. | SK | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React | Current Concern:Performance issues may raise with complex component states and re-renders. Potential Concern: Difficulty in maintaining across multiple components as the application grows. | All
Backend: Node.js and Express | Potential security risks with API endpoints. | All
Database: MongoDB (Atlas) | Current Concern: Schema design can lead to data inconsistency if not carefully planned. Potential Concern: Might be challenging for data retrieval performance for large datasets when application grows. | All
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
GitHub | Repository for version control. Code updates are being pushed regularly.
Microsoft Project Planner | Useful for project scheduling and Gantt charts.
Jira | Jira is helpful for tracking issues, managing agile projects, and promoting teamwork with its customizable workflows and reporting features.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 2
201 | Connect Login/Register page with Artist Profile Page | 1 | SK
202 | Design wireframe for creating Artist Profile Page | 0.5 | TM
203 | Build functionality for Artist Profile Page using React | 1.25 | TM, NJ
205 | Develop backend APIs for profile creation (Node.js) | 1.25 | SK
206 | Setup database tables using MongoDB to store data of artist profile | 1 | SK
207 | Perform manual testing to verify profile creation functionality | 0.25 | All
208 | Build functionality for Edit Profile using React | 1.5 | TM
209 | Develop UI for Edit Profile using React | 1 | TM, NJ
210 | Develop backend APIs for profile editing (Node.js) | 1.5 | SK
211 | Setup database tables using MongoDB to update artist profile | 0.25 | SK
212 | Perform manual testing to verify profile editing functionality | 0.25 | All
213 | Build functionality for Post Creation using React | 1.5 | TM, NJ
215 | Develop backend APIs for creating post (Node.js) | 1.5 | SK
216 | Set up MongoDB collections to store posts | 0.5 | SK
217 | Perform manual testing to verify post creation functionality | 0.25 | All
218 | Design wireframe for Landing/Home page | 0.5 | NJ,TM
219 | Develop UI for Landing/Home page using React | 1.25 | NJ, TM
220 | Develop backend APIs for Landing/Home page (Node.js) | 1.25 | SK
221 | Perform manual tests to verify landing page functionality | 0.25 | All
Medium Priority
222 | Integrate the frontend and backend systems for the Profile Creation feature. | 1 | SK
223 | Integrate the frontend and backend systems to ensure smooth operation for the Post Creation feature. | 1 | SK
224 | Integrate the frontend and backend systems to ensure smooth operation for the Edit Profile feature. | 1 | SK
225 | Integrate the frontend and backend systems to ensure smooth operation for the Landing/Home Page. | 1 | SK
Low Priority
226 | Design and develop user interface for Post Deletion (React) | 1 | TM, NJ
227 | Build the post deletion feature with Node.js | 1 | SK
228 | Develop backend APIs for post deletion | 0.5 | SK
229 | Set up MongoDB collections to delete posts | 0.25 | SK
230 | Perform unit and integration tests to verify post deletion functionality | 0.5 | All
231 | Design and develop user interface for Profile Deletion (React) | 1 | TM, NJ
232 | Build the Profile deletion feature with Node.js | 1 | SK
233 | Develop backend APIs for Profile deletion | 0.5 | SK
234 | Set up MongoDB collections to delete user profile | 0.25 | SK
235 | Perform manual testing to verify profile deletion functionality | 0.25 | All

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 0 | 0
Total Project Hours |  | 0

## Iteration 3 Plan
Iteration Plan 3
Project | Indie Fusion
Team Names: | Sruthi Kamisetti, Twinkle Mishra, Naina Jagiasi
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | Design and create wireframes for Artist Search and Collaboration Requests pages. | TM | Yes
2 | Develop the toggle availability functionality (Yes/No) for artist's profiles, allowing them to set collaboration status. | NJ | Yes
3 | Implement location based artist search filter for users to search artists by location. | NJ | Yes
4 | Create and deploy backend APIs to manage availability status and filter searches for artists based on location. | SK | Yes
5 | Build the Collaboration Request feature for artists, allowing them to send, accept, and reject requests. | NJ | Yes
6 | Design the Collab Requests List Page, displaying received requests with options to accept or reject. | TM | Yes
7 | Develop APIs for collaboration management and list retrieval to support collab request processing and filtering. | SK | Yes
8 | Enhance side navigation bar for improved accessibility, adding sections for search, collaboration, and requests. | SK | Yes
9 | Implement notification system to inform artists of all types of requests, using Node.js and MongoDB. | SK | Yes
10 | Develop an artist specific collaborator list, displaying a group or collaborator list with options for management. | NJ | Yes
11 | Integrate frontend and backend for collaboration and search features, ensuring smooth data flow and usability. | SK | Yes
12 | Perform manual and unit testing on all new features, including availability toggle, search, and collaboration. | All | Yes
13 | Domain Class Diagram: Model core entities such as Artist, Client, CollaborationRequest, Notification, and SearchFilter. | TM | Yes
14 | System Sequence Diagrams: Artist availability toggle, Collaboration request, and Location based search. | TM | Yes
15 | StateChart Diagrams: States for CollaborationRequest (Sent, Pending, Accepted, Rejected), Notification (Created, Sent, Read), and Artist Availability (Available, Unavailable). | SK | Yes
16 | Design Class Diagram: Detailed view of classes and their relationships, focusing on collaboration and search functionality. | TM | Yes
17 | Design Sequence Diagrams: Availability toggle, Collaboration requests (send and manage), and group List retrieval. | NJ | Yes
18 | Navigation Diagram: Map user flows from login to artist search, collaboration requests, notifications, and profile management. | TM | Yes
19 | User Interface Prototype Screens: Artist Profile with Availability Toggle, Search Filters, Collaboration Requests Page, Friends List, Enhanced Navigation Bar. | TM, NJ | Yes
20 | Output Design : For successful/failed actions and notifications for collaboration requests. | SK,TM | Yes
21 | Entity Relationship Diagram (ERD): Tables like Artists, Clients, CollaborationRequests, Notifications, SearchFilters. | TM | Yes
22 | Data Dictionary: Definitions of each table, including field types and constraints (e.g. artist_id, name, location, availability). | SK | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React | Current: Optimizing performance to enhance user experience, particularly with complex component states and re-renders. | All
Potential: As the application grows, establishing clear component structures will facilitate easier maintenance and scalability.
Backend: Node.js and Express | Potential: Enhancing security measures for API endpoints will ensure a robust and secure application, paving the way for reliable user interactions. | All
Database: MongoDB (Atlas) | Current : Careful planning of schema design will promote data consistency and integrity. | All
Potential: As the application expands, implementing effective strategies for data retrieval will enhance performance even with larger datasets.
Tracking Software | Progress & Updates
GitHub | Repository for version control. Code updates are being pushed regularly.
Microsoft Project Planner | Useful for project scheduling and Gantt charts.
Jira | Jira is helpful for tracking issues, managing agile projects, and promoting teamwork with its customizable workflows and reporting features.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
Iteration 3
Medium Priority
Low Priority

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 0 | 0
Total Project Hours |  | 0