## Iteration 1 Plan
Iteration Plan 1
Project | Indie Fusion
Team Names: | Sruthi Kamisetti, Twinkle Mishra, Naina Jagiasi
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | The initial UI for register,login,forgot password and reset password has been completed, outlining all essential tasks and priorities. However, further refinement and polishing of the wireframe are needed to enhance its clarity and user experience before moving forward. | SK/NJ | Yes
2 | Integrate external libraries for React Router for routing, React Bootstrap for styling components, ensuring responsive design | SK | Yes
3 | Create registration feature for new users (artists/clients). Collect required data and handle form validation. | SK/TM | Yes
4 | Create Login functionallity allowing users(Artist/Clients) to sign into their accounts and implement form validation and error handling for login credentials | NJ/TM | Yes
5 | Implement the fogot password feature, where the user can request a password reset link. Validate user and send password reset instructions. | SK/TM | Yes
6 | Develop the rest password feature,allwoing user to set the new password with validation. | NJ/TM | Yes
7 | Setup the backend environment using Nodejs or Java and configure the server, middelware and establish the database connection using MongoDB. | TM | Yes
8 | Develop API endpoints for handling user data such as register,login and password management. | TM | Yes
9 | Perform manual testing on all frontend features(Register,Login,password reset) to ensure proper functionality and user experience. | SK/TM/NJ | Yes
10 | Test frontend and backend integration points to validate successful communication. | SK/TM/NJ | Yes
11 | Document any bugs or issues found during testing and prepare them for next iteration. | SK/TM/NJ | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
React.js for Frontend | Current Concern:Performance issues may raise with complex component states and re-renders. Potential Concern: Difficulty in maintaining across multiple components as the application grows. | SK/NJ
MongoDB for database | Current Concern: Schema design can lead to data inconsistency if not carefully planned. Potential Concern: Might be challenging for data retrieval performance for large datasets when application grows. | TM/SK
Node.js/Java for Backend | Still under discussion. | TM
Solution Design | Ensuring seamless communication between frontend,backend and database could be challenging. | TM/SK/NJ
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Microsoft Project Planner | Useful for project scheduling and Gantt charts.
Jira | Jira is helpful for tracking issues, managing agile projects, and promoting teamwork with its customizable workflows and reporting features.

## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | Refining and polishing of wireframe. | 1.5 | SK/NJ
102 | Registration Module(UI design, API development, Integration) | 20 | SK/TM
103 | Login Module(UI design, API development, Integration) | 16 | NJ/TM
104 | Integrate external libraries for React Router for routing, React Bootstrap for styling components, ensuring responsive design | 0.5 | SK
Iteration 2
Iteration 3
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
105 | Forgot Password Module(UI design, API development, Integration) | 16 | SK/TM
Low Priority (pink)
106 | Reset Password Module(UI design, API development, Integration) | 16 | NJ/TM

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Refining and polishing of wireframe. | 0 | 0.75 | 0 | 0 | 0
102 | Registration Module Frontend UI design | 0 |  | 0 | 0 | 0
103 | Registration Module API development | 0
104 | Registration Module Frontend-Backend Integration | 0
105 | Login Module Frontend UI design | 0 | 20 | 0 | 0 | 0
106 | Login Module API development | 0
107 | Login Module Frontend-Backend Integration | 0
108 | Integrate external libraries for React Router for routing, React Bootstrap for styling components, ensuring responsive design | 0 | 16 | 0 | 0 | 0
109 | Forgot Password Module Frontend UI design | 0 | 16 | 0 | 0 | 0
110 | Forgot Password Module API development | 0
111 | Forgot Password Module Frontend-Backend Integration | 0
112 | Reset Password Module Frontend UI design | 0
113 | Reset Password Module API development | 0
114 | Reset Password Module Frontend-Backend Integration | 0 | 16 | 0 | 0 | 0
115 | Implemented server-side logic to handle logout, including session or token validation and clearing session data on the client-side. | 0
116 | Verify that the logout button functions correctly, ensuring the user is logged out, redirected to the login page, and session data is cleared. | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 275 | 0 | 0 | 0
Total Project Hours |  | 275

## Iteration 2 Plan
Iteration Plan 2
Project | Indie Fusion
Team Names: | Sruthi Kamisetti, Twinkle Mishra, Naina Jagiasi
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | Create a wireframe of the logout feature. | SK/TM/NJ | Yes
2 | Implement and style the logout button in the navigation bar. | SK/TM/NJ | Yes
3 | Develop the UI for the logout feature using React, implementing styles and ensuring it matches the app's design. | SK/TM/NJ | Yes
4 | Implement server-side logic to handle logout, including session or token validation and clearing session data on the client-side. | SK/TM/NJ | Yes
5 | Verify that the logout button functions correctly, ensuring the user is logged out, redirected to the login page, and session data is cleared. | SK/TM/NJ | Yes
6 | Create wireframes for the Landing/Home page, including sections for the hero area, , platform overview, and featured artists. | SK/TM/NJ | Yes
7 | Implement the landing page layout based on wireframes, including responsive design elements for the hero section and styling for and other sections. | SK/TM/NJ | Yes
8 | Set up backend API endpoints to fetch featured artists and testimonials for display on the landing page. | SK/TM/NJ | Yes
9 | Conduct manual testing to ensure all UI elements are responsive, the CTA buttons function as intended, and all sections of the page load properly. | SK/TM/NJ | Yes
10 | Design and create wireframe for artist profile page layout. | SK/TM/NJ | Yes
11 | Implement the artist profile functionality using React, allowing artists to create and edit profiles, including fields for name, bio, skills, and location. | SK/TM/NJ | Yes
12 | Create the database structure in MongoDB to store artist data and implement necessary API endpoints. | SK/TM/NJ | Yes
13 | Verify the profile creation and editing functionality works as expected, ensuring data is correctly saved and displayed. | SK/TM/NJ | Yes
14 | Develop a Use Case Diagram representing major system interactions for both artists and clients (who can also be artists), highlighting functionalities like profile creation, collaboration requests, and searching for artists. | SK/TM/NJ | Yes
15 | Document any bugs or issues found during testing and prepare them for the next iteration. | SK/TM/NJ | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React | Need to ensure consistent UI across devices. | SK/TM/NJ
Backend: Node.js and Express | Potential security risks with API endpoints. | SK/TM/NJ
Database: MongoDB (Atlas) | Scalability issues as user data grows | SK/TM/NJ
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
GitHub | Repository for version control. Code updates are being pushed regularly.
Microsoft Project Planner | Useful for project scheduling and Gantt charts.
Jira | Jira is helpful for tracking issues, managing agile projects, and promoting teamwork with its customizable workflows and reporting features.

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Post Creation:Users can create a post with both text and an image. The post can either be a collaboration post or a personal post.
Display Posts: The created post will be displayed with a "Request" button if it is marked as a collaboration post.
Request Feature: Users can request to collaborate by providing their email, mobile number, and a message when sending the request.
Edit Post: Users have the ability to edit an existing post.
Delete Post: Users can delete their post.
UI Implementation: User interface design and implementation for post creation, display, and actions.
Develop APIs to handle post creation
Develop APIs to handle Display
Develop APIs to handle editing
Develop APIs to handle post creation, display, editing, deleting, and collaboration requests.
Iteration 2
Iteration 3
Medium Priority
Low Priority

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 0 | 0
Total Project Hours |  | 0

## Iteration 3 Plan
Iteration Plan 3
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
Iteration 3
Medium Priority
Low Priority

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 0 | 0
Total Project Hours |  | 0